## Features
VideoEditor (working title)

Feature	Beginner	Full	Status

Reading and rendering	yes	yes	done
Editing start/end/offset	yes	yes	done
Mixing audio	yes	yes	done
Geometry	yes	yes	todo
Transparency / z-Order	yes	yes	todo
Multi Monitor	no	yes	todo
Second Preview (Colour grading)	no	yes	todo
Audio synchronised grid	yes	yes	todo
Auto colour matching		yes	todo
Object select/cut out/following	yes	yes	todo
Multiple Edits in one project	no	yes	todo

Hosting Audio effects
Loading 3rd party effects	yes	yes	done
Automation	yes	yes	done
Automation graphs	yes	yes	needs improvement
drag-drop effects	yes	yes	done
Latency compensation	yes	yes	todo
Preset library	yes	yes	todo
Audio aux tracks	no	yes	todo
Send to tracks (reverb)	no	yes	todo
Surround formats	no	yes	todo
Audio Multi-threading			todo
Record audio (voice over)	yes	yes	todo
Display generated waveform	yes	yes	todo

Hosting video effects
Built-in	yes	yes	done
OpenFX			todo
Render in OpenGL	yes	yes	todo

Render Video to File

MP4 – H.264/H.265	yes	yes	buggy
R3D	no	yes	todo
Apple ProRes	no	yes	todo
WMV	yes	yes	todo

## Shortcuts
VideoEditor (working title)

Keyboard shortcuts
New Project	CMD+N	direct
Open Project	CMD+O	dialog
Save Project	CMD+S	direct
Render Video	CMD+R	dialog
Preferences	CMD+,	dialog

Undo	CMD+Z	direct
Redo	CMD+Shift+Z	direct
Delete selected clip	Backspace	direct
Copy	CMD+C	no function yet
Paste	CMD+V	no function yet
Splice (cut clip)	CMD+B	direct
Visible / mute	v	direct

Play/Pause	Space	direct
Return to zero	Return	direct

Preview full size	CMD+Return	direct
End full size	ESC	direct

## UX-bugs
VideoEditor (working title)

UX-Bugs

Plugin scanning has no feedback
No way to exclude crashed plugins
Select individual automation curves
horizontal drag: magnetic? grid?
Drag multiple images: add as sequence